## Sheet1
December
| 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| S | S | M | T | W | TH | F | S | S
Setup for front end (React Js)
Setup Supabase
Add Login/Sign Up Button
SignUp form
Validation for SignUp | bar: December 12 S
Integrate in Supabase | bar: December 12 S
Login Form | bar: December 13 M
Integrate Login in Supabase,
Design card for products